## Slide 1: Project management/planning

## Slide 2: Study Objectives
By the end of this unit, the learner should be able to:
Describe the principles, concepts, the importance of planning, project planning, proposal writing; types of plans- strategic plans, annual operational plans, annual departmental and individual plans; project planning process- cycle, situation analysis, feedback, prioritisation, developing implementation plans, budgeting, techniques for public involvement

## Slide 3: Introduction to Health Project Management – Project and Programme
Project: a set of inter-related activities carried out in a defined geographic area or technical sector over a specified period of time towards the achievement of specific outcomes or objectives.
Involves the mobilization, organization and control of different resources for the performance of the activities
The coverage of a project may be a small part of a country, such as a district or county, and the scope may be a single sector or a sub-sector.

## Slide 4
A project has a small number of activities and is time limited to about 3-5 years, achievement of the objectives determines the end of the project.
However, unlike industrial projects, health projects normally do not close down but continue with renewed emphasis on new objective targets or changed strategies.

## Slide 5: programme
A Programme may be defined as a series, usually a large number, of activities carried out in a defined geographic area or technical sector over a long period of time towards the achievement of specific impact or goal.
A collection of projects grouped and implemented simultaneously or serially over long duration towards a common goal constitute a programme.
The coverage of a programme is usually a whole country or region and the scope is inclusive several technical sectors.
The programme has no strict time limit and may run for years or decades.

## Slide 6: Comparison between Project and Programme
Project | Programme
Specific objectives | Broad goal(s)
Small number of activities | Large number of activities in Several Projects
Short duration (Short-term / Time limited) | Long duration (Long-term / No strict time limit)
Limited coverage (geographic area) | Wide coverage
Limited scope (technical sector or sub-sector) | Wide scope

## Slide 7: Elements of a project
Goal: A broad statement of the situation or change in status desired to be achieved in the future. A goal has no specific magnitude and no strict time limit during which it will be achieved. Indeed, it may not be achieved at all!
Objective: A statement of specific outcomes desired to be achieved in a specific geographic area during a specified period of time. An objective normally has a specific target population or beneficiaries, whose needs must be compatible with the objectives.
Strategy: A strategy is the means or way how the goals and objectives will be met. It specifies the general approach that will be used towards the achievement of the goals and objectives of a programme or project.
Activity: Activities are the project processes involving actions or things that have to be done (doables) in order to achieve the goals and objectives of a project or programme.

## Slide 8: Elements of a project
Inputs: These are the resources required and utilized for conducting an activity / process.
For example, in immunization, the inputs are the technical and non-technical staff, the children, the vaccines and the supplies and equipment and logistics.
Outputs: These are the products resulting from conducting an activity / process. In immunization, the outputs are the children immunized.
Outcome: This is the external effect of the outputs of the activity / process. In immunization this is the immunization coverage in the community, i.e. the proportion of children in the community who are immunized. The project objective is a measure of its outcome.
Impact: This is the ultimate effect of the activity as indicated by desired change in status specified in the goal. In immunization, this is the reduction in morbidity and mortality from the immunization related disease. The project goal is a measure of its impact.

## Slide 9: The Project Life Cycle
A programme may be implemented through serial or parallel projects. The programme process is continuous, running beyond the time limits of the project.
Thus, the project and programme may be depicted as cyclic processes of repetitive events that start with planning and end with re-planning.
This is referred to as the project (or programme) cycle, composed of defined phases, that is:
          Conceptualization
          Prioritization
          Planning and organization,
          Implementation
          Monitoring and evaluation.

## Slide 10: The Health Project Cycle
Situation Analysis / Needs Assessment / Problem Identification
Prioritization, and setting goals and objectives
Feedback &
Re-planning
Monitoring & Evaluation
Identification, Appraisal & Prioritization of Interventions
Implementation

## Slide 11: The Project Activity Process
Health care activity processes are similar to business and industrial processes in terms of the activity flow.
However differ in terms of their specific inputs, outputs, outcomes and impact.
While industrial process involve non-human materials that are convertible into commodity products, health care processes use on human beings whose condition is changed by the processes of care.
However the concepts and principles of processes in industry and business are applicable in health care processes.
Input
Outcomes (project objectives)
Impact (project goal)
Outputs
Process
(strategic activities)

## Slide 12: Introduction to Health Project Management
Definition of Management: Management may be defined as “the process of getting things done through people”.
It refers to both the system and processes of getting things done. Thus, the top leadership of an organization is referred to as the management of the organization.
Likewise, the process of planning, organizing, leading or coordinating activities and controlling resources towards achievement of specific goals and objectives is referred to as management.

## Slide 13
There are two key principles of the management process:
Commitment to purposeful action for the achievement of specific objectives;
Recognition of people as an important resource for getting things done.

## Slide 14: Introduction to Health Project Management cont’
Administration: Is the process or system of directing and controlling of the operations or affairs of an organization or business in accordance to and strict adherence to set rules and regulation.
The purpose of administration is to ensure implementation of activities follows organizational policies and involves supervision and monitoring based on the set rules and regulations of the organizations.

## Slide 15: Purpose of Management
The major concern and purpose of management is to ensure effectiveness, efficiency and sustainable achievement of organizational goals and objectives.
These factors determine whether or not the intended outcomes of the processes applied satisfy or meet the needs of the organization and its stakeholders.
Effectiveness refers to the ability of the project processes to achieve the intended outcomes among the target population.
Efficiency refers to the extent to which the project process maximizes the utilization of resources available to bring about its outcomes. It compares outcomes with resources utilization in terms of cost per activity.

## Slide 16: Purpose of Management
Sustainability in project management refers to the continued benefit by the beneficiary community as a result of project implementation.
This results from the community taking over and continuing implementation of the core project activities, and the results of the project are maintained by the community’s own actions.
This is possible when the community has been involved from the onset of the project and its capacity (knowledge, attitudes, skills, technology and structures) developed during the entire duration of the project, enabling them to continue the management of the activities initiated by the project.

## Slide 17
Authority and Responsibility
Authority refers to the powers bestowed upon persons in positions with management and administrative functions enabling them to get people to do things and to control the utilization of resources.
Responsibility refers to the obligation of subordinates to their superiors relating to the results of work expected of them.
Subordinates take responsibility for their work and those higher up take responsibility for activities of those below them in the management system.

## Slide 18: Purpose of Management cont’
Functions of Management
The management process involves a sequential performance of key functions of planning, implementation and evaluation that are performed in a continuous manner.
It also involves the performance of supportive functions of leadership and team building, decision making and delegation, motivation and communication, and directing and controlling that are performed continuously during the project cycle.

## Slide 19: Functions of Management
Diagrammatic Representation of the Key Functions of Management
Evaluation planning
implementation

## Slide 20: Key Functions of Management
Planning may be defined as a process of making decisions for the future or assessing the current situation, setting goals and objectives, and putting in place interventions (scheme or method) for achieving the objectives.
Evaluation is defined as the periodic assessment of the level of achievement of the project goal and objectives
Monitoring is the continuous assessment of the performance of project activities during implementation. It is the systematic and continuous review of progress against planned activities and targets

## Slide 21: Supportive Functions
Name some supportive functions of management covered under leadership and management

## Slide 22: Modern Organizational Management
Projects and programmes are the domain of, and are implemented within the context of organizations.
An organization is a framework or an arrangement established, with specific responsibilities, authority and duties, to facilitate the mobilization of resources and coordination of their utilization for the achievement of specific goals and objectives.

## Slide 23: Project Planning
Project planning is a procedural step in project management, where required documentation is created to ensure successful project completion.
Documentation includes all actions required to define, prepare, integrate and coordinate additional plans.
The project plan clearly defines how the project is executed, monitored, controlled and closed.

## Slide 24: PLANNING PROCESS
Has 8 interrelated steps
ANALYSIS OF SITUATION
PRIORITY SETTING
GOALS AND OBJECTIVES
FORMULATION OF STRATEGIES
CHOICES OF STRATEGIES
PLAN OF ACTION
IMPLEMENTATION
EVALUATION

## Slide 25: Summarized into 4 steps viz:-
Assessment →Setting goals →Implementation→ Evaluation
step 1:SWOT & PEST analyses
SWOT Analysis is a useful technique for understanding your Strengths and Weaknesses, and for identifying both the Opportunities open to you and the Threats you face.
PEST Analysis is a simple and widely used tool that helps you analyze the Political, Economic, Socio-Cultural, and Technological changes in your business environment.
This helps you understand the "big picture" forces of change that you're exposed to, and, from this, take advantage of the opportunities that they present.

## Slide 26: Summarized into 4 steps viz:-
Step 2:List of all issues & criteria for prioritization.
Step 3:SMART
Step 4:Quiz HOW?; review obstacles and limitations related to resources and environment.
Step 5:Explore all available alternatives and make criteria for choosing a strategy.i.e:
    Most important
    Most urgent
    Least costly
    Most easily achieved
    Acceptable to the community

## Slide 27: Cont’
STEP 6:Ensuring implementation
What to be done, how to be done, sequence (which one1st ?), place of action,who to do and when to take place.
Step 7:-Observation, Information gathering, supervision, documentation etc
Step 8:Judging,appraising,determining the worth/value/ quality of programme in terms of: Relevance, Effectiveness, Efficiency and Impact .

## Slide 28: Characteristics of Objectives - SMART
  Specific: identifies concrete events or actions that will take place
  Measurable: quantifies the amount of resources, activity, or change to be expended and achieved
  Appropriate: logically relates to the overall problem statement and desired effects of the program
  Realistic: Provides a realistic dimension that can be achieved with the available resources and plans for implementation
  Time-based: specifies a time within which the objective will be achieved

## Slide 29: PRINCIPLES OF PLANNING
Needs based-Public/client/patient demands
Resource based-Human and material
Value based-Ethical considerations
Evidence based-Availability of valid & reliable facts
Opinion based-Consider peoples perceptions; positive and negative

## Slide 30: Proposal writing
A proposal is a plan or an idea, often a formal or written one, which is suggested for people to think about and decide upon

## Slide 31: Planning Your Proposal
Define your audience. You need to make sure that you think about your audience and what they might already know or not know about your topic before you begin writing.
Define your issue. It is clear to you what the issue is, but is that also clear to your reader?
Define your solution. This should be straightforward and easy to understand. Once you set the issue you're addressing, how would you like to solve it? Get it as narrow (and doable) as possible.

## Slide 32: Planning Your Proposal cont’
Keep elements of style in mind. Depending on your proposal and who'll be reading it, you need to cater your paper to fit a certain style. What do they expect? Are they interested in your problem?
Make an outline. This will not be part of the final proposal, but it will help you organize your thoughts. Make sure you know all of the relevant details before you start

## Slide 33: Planning Your Proposal cont’
Once you know what kind of proposal you’re writing you need to research and plan out the document to make sure you don’t miss out any vital information.
Although what you write will vary a little depending on the type of proposal you’re submitting and the format it’s using, you’ll generally want to:
Define your audience
Know what problem the proposal tackles
Research the current state of the issue
Clearly define the proposal
Predict the effect this will have
Assess the time and resources this will take
Create an outline of the document

## Slide 34: Writing Proposal
Start with a firm introduction. This should start out with a hook. Ideally, you want your readers enraptured from point one. Make your proposal as purposeful and useful as possible. Use some background information to get your readers in the zone. Then state the purpose of your proposal
State the problem. After the introduction, you'll get into the body, the meat of your work. Here's where you should state your problem. What is the problem? What is causing the problem? What effects does this problem have

## Slide 35: Writing Proposal cont’
Propose solutions. This is the most important part of your proposal. The solutions section is where you get into how you will address the problem, why you will do it in this way, and what the outcomes will be.
Include a schedule and budget. Your proposal represents an investment. In order to convince your readers that you're a good investment, provide as much detailed, concrete information about your timeline and budget as possible

## Slide 36: Writing Proposal cont’
Wrap up with a conclusion. This should mirror your introduction, succinctly wrapping up your general message. If there are consequences to your proposal not being undertaken, address them. Summarize the benefits of your proposal and drive home that the benefits outweigh the costs. Leave your audience thinking ahead. And, as always, thank them for their consideration and time
Edit your work. Be meticulous in writing, editing, and designing the proposal. Revise as necessary to make it clear and concise, ask others to critique and edit it, and make sure the presentation is attractive and engaging as well as well organized and helpful
Proofread your work. Editing focuses on getting the content as clear and concise as you can make it. Proofreading makes sure that your content is free of mistakes. Go over your proposal carefully to catch any spelling, grammar, or punctuation errors.

## Slide 37: Types of Proposals
Pre-Proposal
Solicited Proposal
Renewal and Continuation Proposals
Limited Submissions
Revised Budgets

## Slide 38
Pre-Proposal
A pre-proposal (sometimes called a white paper, letter proposal, letter of intent, preliminary proposal, pre-application, or concept paper) is a short description of the proposed project.
Its purpose is to inform and interest the potential sponsor in the project, resulting in a request for a more detailed formal proposal.

## Slide 39: Solicited Proposal
Sponsors solicit formal proposals by publishing specific program announcements.
These solicitations are often called Request for Proposals (RFPs), Funding Opportunity Announcements (FOAs), Broad Agency Announcements (BAAs), etc. Researchers responding to the program announcement write the proposal to meet the sponsor’s program guidelines. Deadlines may recur annually or several times a year.
Most RFP’s have a stated deadline and are one-time solicitations for specific needs of the sponsor, not expected to recur.
The proposed project must respond to the specific work statement in the Request for Proposal.
Solicited proposals must be routed through the University proposal routing process prior to submitting the proposal to the sponsor.

## Slide 40: Renewal and Continuation Proposals
A competing renewal proposal (also called a competing continuation) is a request for continued funding of a project for which the funding or project period is about to terminate. Such proposals are similar to "new" proposals and must be routed and approved in the same manner.
Noncompeting continuation proposals, which request the next year’s funding within a multi-year grant, generally consist of a progress report, budget, and other relevant materials such as research results, reprints, vitae for new personnel, etc. They sometimes include a financial status report showing the unobligated balance for the current year.
Research Performance Progress Reports (RPPR) is a federal-wide uniform progress report format for use by federal agencies that provide sponsored funding. RPPR is also used for noncompeting continuations.

## Slide 41: Limited Solicitations
Occasionally, sponsors announce program funding opportunities limiting the number of proposals that may be submitted by each institution/applicant.
Faculty interested in submitting proposals should follow the limited submission pre-proposal process.
The primary criterion for selecting proposals is the relevance to the program selection criteria and the potential for successfully competing in the sponsor’s competitive process.
Faculty whose pre-proposals are selected as the institutional submission will be notified and must then prepare a complete application to submit to the sponsor.

## Slide 42: Revised Budgets
When a sponsor wants to fund a proposed project at an amount different from that originally proposed, the sponsor asks the investigator to submit a "revised" budget supporting the amount to be funded.
A revised budget must be routed through the University proposal routing process to document the signatories’ approval of the budget revisions.
If the sponsor reduces the budget, the investigator must determine whether the originally proposed scope and objectives of the project can be met under the revised budget.
If not, the investigator and sponsor must redefine the scope and objectives in writing before the University accepts the award.
If the original budget contained cost share or matching, the cost share or matching amount may need to change to reflect the budget revisions.

## Slide 43: Budget
A budget is a statement of expected results the managers expect from the company.
Types of budgets
Financial budgets include balance sheets, income/expense statements, and statements of cash flow.
Operating budgets project revenue against expenditures.
Nonmonetary budgets allocate resources such as labor, workspace, and equipment use.
Fixed budgets are budgets that do not change with increased or decreased activities, such as sales revenue. They are also called static budgets.
Flexible budgets will vary with the level of activity (grow or be reduced according to changing conditions).

## Slide 44: Types of plan
'Those who fail to plan, plan to fail‘
There are three main types of plans that a manager will use in his or her pursuit of company goals, which include operational, tactical and strategic
Operational plans are necessary to attain tactical plans and tactical plans lead to the achievement of strategic plans

## Slide 45: Strategic plans
They are designed with the entire organization in mind and begin with an organization's mission.
Top-level managers, such as CEOs or presidents, will design and execute strategic plans to paint a picture of the desired future and long-term goals of the organization.
Essentially, strategic plans look ahead to where the organization wants to be in three, five, even ten years.
Strategic plans, provided by top-level managers, serve as the framework for lower-level planning.

## Slide 46: Tactical plans
They support strategic plans by translating them into specific plans relevant to a distinct area of the organization.
Tactical plans are concerned with the responsibility and functionality of lower-level departments to fulfill their parts of the strategic plan

## Slide 47: Operational plans
They are the plans that are made by frontline, or low-level, managers.
All operational plans are focused on the specific procedures and processes that occur within the lowest levels of the organization.
Managers must plan the routine tasks of the department using a high level of detail like scheduling employees each week; assessing, ordering and stocking inventory; creating a monthly budget or outlining an employee's performance goals for the year.
Operational plans can be either single-use or ongoing plans
Single-use plans are those plans that are intended to be used only once.
They include activities that would not be repeated and often have an expiration like Creating a monthly budget and developing a promotional advertisement for the quarter to increase the sales of a certain product

## Slide 48
Annual Operation Planning (AOP) is a detailed projection of all estimated income and expenses based on forecasted sales revenue during one year to identify, communicate and monitor progress on key priorities for the year that advance the strategic plan